## Slide 1
PROJECT UPDATE
IEEE 1687 / 1838 Tessent Integration Flow
Third-party Tessent integrated into the existing RTL-to-gate design environment.
6
CORE STEPS
CURRENT BASELINE
1
ENV
2
INSERT
3
RETARGET
4
RTL VERIFY
5
SYNTHESIS
6
GATE VERIFY
Current: access flow and generated patterns verified | Next: ATPG and regression | Bonus: Steps 10–11
IEEE 1687 / 1838 Automation Progress Review
01

## Slide 2
PROJECT CONTRIBUTIONS
Project Contributions
Tessent integration establishes a verified IEEE 1687 / 1838 flow
without replacing the existing RTL-to-gate environment.
01 INTEGRATE
Flow integration
Tessent + RTL-to-gate
02 VERIFY
Three access scopes
1687 · +1838 · stack_top
03 DELIVER
Working Tcl + evidence
scripts · compare · issue guide
CURRENT PROOF
Access and pattern delivery are proven; the ATPG environment is the next milestone.
Architecture based on the current prototype and IEEE 1687-2014 / IEEE 1838-2019
02

## Slide 3
HOW TO READ THE DECK
Current Flow Produces Evidence and Documentation
1
CURRENT FLOW
Configure Each Case
Working Tcl set; I/O, hierarchy, and checks remain case-specific
2
AUTOMATE
Run + Check
Run flow · DRC · path reachable · mismatch = 0
3
EVIDENCE
Save Results
Logs · waveforms · reports · comparisons
DOCUMENTED
Tcl scripts + issue resolutions + verification evidence
Step 12 will consolidate scripts, design settings, folders, and rerun rules.
Validated: IEEE 1687 · IEEE 1687 + 1838 · stack_top | DWR = bonus
03

## Slide 4
BASELINE
Six Core Steps Define the Current Baseline
01
Environment
scripts + inputs
02
RTL Insertion
1687 / 1838
03
ICL / PDL
package pattern
04
RTL Verify
waveform + compare
05
Synthesis
preserve network
06
Gate Verify
RTL = gate
Validated Access | Current Deliverables
FLOW INTEGRATION Tessent linked to existing RTL, simulation, and synthesis
WORKING TCL SET Executable scripts; design settings are still mixed in one folder
DOCUMENTATION Tcl usage, integration issues, fixes, and verification evidence
Validated: IEEE 1687 · IEEE 1687 + 1838 · stack_top | DWR = bonus
04
Current assets: working Tcl · ICL / PDL · simulation · synthesis Step 12: separate common flow, design config, runs, and reports

## Slide 5
SCALE
One Framework Supports Three Access Scopes
Current assets: working Tcl · ICL / PDL · simulation · synthesis Step 12: separate common flow, design config, runs, and reports
Validated: IEEE 1687 · IEEE 1687 + 1838 · stack_top | DWR = bonus
05
LEVEL 1
IEEE 1687
TAP → SIB → TDR → Instrument
LEVEL 2
1687 + IEEE 1838
PTAP / 3DCR / STAP + local IJTAG
LEVEL 3
Stack top
Multiple STAPs + hierarchical retargeting
+ wrapper control
+ multi-die access depth

## Slide 6
STAGE DETAIL
Step 1 Establishes a Working Run Environment
1 ENV
2 INSERT
3 RETARGET
4 RTL VERIFY
5 SYNTHESIS
6 GATE VERIFY
Validated: IEEE 1687 · IEEE 1687 + 1838 · stack_top | DWR = bonus
06
STAGE 1
Run Environment
TASK
Build
CHECKPOINT
Must Pass
EVIDENCE
Show
Organize RTL, libraries, and file lists
Run the existing Tcl scripts from one working folder
Edit design I/O, hierarchy, and checks case by case
✓
RTL elaborates cleanly
✓
Required Tcl sequence runs successfully
✓
Expected artifacts are generated
Current run log
Executed script sequence + outputs
Working Tcl folder
Scripts + design-specific edits together
Generated artifacts
RTL · ICL · patterns · reports

## Slide 7
STAGE DETAIL
Step 2 Inserts Tessent Test Logic into Existing RTL
1 ENV
2 INSERT
3 RETARGET
4 RTL VERIFY
5 SYNTHESIS
6 GATE VERIFY
Validated: IEEE 1687 · IEEE 1687 + 1838 · stack_top | DWR = bonus
07
STAGE 2
RTL Insertion
Existing RTL
RTL + libraries + instrument ports
Tessent Test Network
TAP / PTAP
SIB
TDR
3DCR
STAP
Checkpoint
✓
Insertion DRC passes
✓
All instruments are reachable
✓
Hierarchy matches the architecture
Evidence
Insertion summary
Hierarchy report
Connectivity report
Insertion is complete only when reachability is proven.

## Slide 8
STAGE DETAIL
Step 3 Retargets PDL to the Package Path
1 ENV
2 INSERT
3 RETARGET
4 RTL VERIFY
5 SYNTHESIS
6 GATE VERIFY
Validated: IEEE 1687 · IEEE 1687 + 1838 · stack_top | DWR = bonus
08
STAGE 3
PDL Retargeting
Instrument PDL
write · run · read
Post-insertion ICL
network hierarchy
Retargeting
resolve path
Top-level Pattern
package pattern
Checkpoint
✓
ICL checks pass
✓
No unresolved paths
✓
Scan length matches the network
Why it matters
Tessent resolves the access hierarchy; design-specific Tcl maps each design's ports and instruments.

## Slide 9
STAGE DETAIL
Step 4 Verifies the Full Access Sequence
1 ENV
2 INSERT
3 RETARGET
4 RTL VERIFY
5 SYNTHESIS
6 GATE VERIFY
Validated: IEEE 1687 · IEEE 1687 + 1838 · stack_top | DWR = bonus
09
STAGE 4
RTL Access Verification
TMS / TCK
drive state
TAP / PTAP
change state
IR decode
select path
Capture / Shift / Update
apply controls
SIB / 3DCR / STAP
open network
TDR / shadow
write & read
PASS criteria
✓
All care bits match
✓
Instrument response is correct
✓
Unselected instruments stay unchanged
Evidence
Waveform with event markers
PASS summary · mismatch = 0
Reset · SIB / STAP close

## Slide 10
RTL RESULTS
One Pattern Flow Covers All Three Levels
1 ENV
2 INSERT
3 RETARGET
4 RTL VERIFY
5 SYNTHESIS
6 GATE VERIFY
Validated: IEEE 1687 · IEEE 1687 + 1838 · stack_top | DWR = bonus
10
01
IEEE 1687
TAP → SIB → TDR → Instrument
Local access confirmed
✓
02
1687 + IEEE 1838
PTAP → local SIB → TDR
Wrapper controls confirmed
✓
03
stack_top
Package → Basic STAP → Sensor STAP → SIB → TDR
Stack path + return confirmed
✓
Access depth grows; pattern authoring stays simple.

## Slide 11
WAVEFORM EVIDENCE
Event Markers Make Stack Traces Debuggable
1 ENV
2 INSERT
3 RETARGET
4 RTL VERIFY
5 SYNTHESIS
6 GATE VERIFY
Validated: IEEE 1687 · IEEE 1687 + 1838 · stack_top | DWR = bonus
11
M0
Reset
M1
Basic 3DCR
M2
Sensor0 3DCR
M3
Sensor1 SIB
M4
TDR Update
M5
Start
M7
Valid
M8
Capture
M9
Compare
M10
Pass
Markers localize failures to 1838 access, 1687 selection, or instrument response.

## Slide 12
STAGE DETAIL
Step 5 Preserves the Test Network Through Synthesis
1 ENV
2 INSERT
3 RETARGET
4 RTL VERIFY
5 SYNTHESIS
6 GATE VERIFY
Validated: IEEE 1687 · IEEE 1687 + 1838 · stack_top | DWR = bonus
12
STAGE 5
Synthesis
Tessent RTL
test logic
Compile test block
separate block
dont_touch + SDC
preserve + constrain
Top synthesis
full design
Gate netlist
GLS ready
Checkpoint
✓
Test network survives optimization
✓
Test clocks, resets, and constraints are applied
Evidence
Pre/post hierarchy comparison
Log · constraints · gate netlist

## Slide 13
STAGE DETAIL
Step 6 Verifies RTL–Gate Response Matching
1 ENV
2 INSERT
3 RETARGET
4 RTL VERIFY
5 SYNTHESIS
6 GATE VERIFY
Validated: IEEE 1687 · IEEE 1687 + 1838 · stack_top | DWR = bonus
13
STAGE 6
Gate Verification
RTL lane
Gate lane
Inserted RTL
Same pattern
Expected response
Gate netlist + libs
Same pattern
Observed response
COMPARE
care-bit mismatch = 0
Netlist compiles • pattern completes • care-bit mismatch = 0

## Slide 14
FLOW VALIDATION
The Current Six-Step Baseline Is Verified at All Levels
Columns = access levels · rows = accepted deliverables
DWR bonus
Verification item | 1687 | 1687 + 1838 | stack_top
Automated RTL insertion | ✓ | ✓ | ✓
ICL generation / check | ✓ | ✓ | ✓
PDL retargeting | ✓ | ✓ | ✓
RTL pattern simulation | ✓ | ✓ | ✓
Synthesis integration | ✓ | ✓ | ✓
Gate-level pattern simulation | ✓ | ✓ | ✓
Hierarchical access | N/A | Local die | Multi-die
Auto-generated patterns are verified across the current access scopes.
Validated: IEEE 1687 · IEEE 1687 + 1838 · stack_top | DWR = bonus
14

## Slide 15
ENGINEERING VALUE
The Baseline Is Integrated, Verified, and Documented
01
INTEGRATED
Tessent works inside the existing RTL-to-gate environment
02
VERIFIED
Generated patterns pass through local, wrapper, and stack access
03
DOCUMENTED
Capture scripts, issues, fixes, checkpoints, and evidence
Packaged Deliverables
Integration flow
Tessent + simulation + synthesis handoff
Working Tcl + document
scripts + issue / solution guide + evidence
Step 12 will organize the working Tcl set into a maintainable handoff environment.
Validated: IEEE 1687 · IEEE 1687 + 1838 · stack_top | DWR = bonus
15

## Slide 16
ROADMAP
Pattern Verification Leads to ATPG and Flow Consolidation
Next: build the ATPG environment; Steps 10–11 are bonus; Step 12 organizes the execution flow.
16
VERIFIED ACCESS BASELINE
STEP 12 · FLOW CONSOLIDATION
NEXT TARGET · ATPG FLOW
01
✓
Environment
scripts ready
02
✓
RTL Insertion
network inserted
03
✓
ICL / PDL
paths retargeted
04
✓
RTL Verify
mismatch = 0
05
✓
Synthesis
network preserved
06
✓
Gate Verify
RTL = gate
12
Flow Cleanup
Tcl + folders
11
DWR Test
additional bonus
10
Sensor Scan
additional bonus
09
Regression
coverage + PASS/FAIL
08
ATPG Flow
generate + grade
07
Pattern Verify
generated · verified
13
GUI / VISUAL REPORT
Run Tcl · track status · export PASS/FAIL, coverage, mismatch, and runtime

## Slide 17
NEXT TARGET
Next Milestone: Build a Verifiable ATPG Environment
7 PATTERN VERIFY
8 ATPG FLOW
9 REGRESSION
10 SENSOR SCAN
11 DWR TEST
12 ENV CLEANUP
Scope: die-level ATPG generation and grading; stack-level hierarchical pattern delivery
17
NEXT TARGET
ATPG Generation, Fault Grading & Regression
Auto Patterns
generated + verified
ATPG Generation
representative faults
Fault Grading
fault simulation + coverage
Regression
coverage + PASS / FAIL
Checkpoint
✓
Auto-generated patterns pass access and compare
○
ATPG patterns and fault coverage reported
○
Fault grading and regression return PASS / FAIL
Why it matters
The next milestone connects ATPG generation, fault grading, coverage, and regression in one environment.

## Slide 18
ADDITIONAL BONUS
Steps 10–11 Extend Sensor and Die-Link Testing
7 PATTERN VERIFY
8 ATPG FLOW
9 REGRESSION
10 SENSOR SCAN
11 DWR TEST
12 ENV CLEANUP
Additional bonus: sensor structural ATPG and DWR interconnect testing
18
ADDITIONAL BONUS
Sensor Scan & DWR Interconnect Test
Sensor + Die Links
sensor logic + die links
DFT Extensions
Sensor Scan
DWR
Stuck-at
Transition
Die-link Test
Checkpoint
✓
Sensor structural coverage reported
✓
DWR tests die-to-die faults
✓
Run only if schedule and die-link ports permit
Evidence
Scan + ATPG report
DWR coverage
Die-link simulation
Additional bonus does not block the main ATPG environment deliverable.

## Slide 19
FLOW CONSOLIDATION
Step 12 Consolidates the Tcl and Run Environment
1 INVENTORY
2 COMMON FLOW
3 DESIGN CONFIG
4 RUN FOLDERS
5 CHECKS
6 HANDOFF
GUI can follow after outputs, folders, and PASS / FAIL rules stabilize.
19
STEP 12
Environment Consolidation
Current State
all Tcl scripts in one working folder
Target Structure
common/
designs/
runs/
docs/
reports/
Checkpoint
✓
Separate common flow from design-specific settings
✓
Define one documented run order and entry point
✓
Reproduce key results from a clean output folder
Evidence
Folder tree
Config + entry script
Clean-run checklist
Step 12 turns working scripts into a maintainable, transferable environment.

## Slide 20
CURRENT STATUS
Next Milestone: A Verifiable ATPG Environment
✓
ENV
✓
INSERT
✓
RETARGET
✓
RTL VERIFY
✓
SYNTHESIS
✓
GATE VERIFY
VERIFIED BASELINE
✓
Tessent integrated into the existing design environment
✓
Six-step access baseline verified at three levels
✓
Auto-generated patterns verified through the current access flow
NEXT TARGET
Generate ATPG patterns and perform fault grading
Report fault simulation, coverage, and regression
Step 12: consolidate Tcl, configs, folders, and rerun rules
Next: ATPG generation, grading, coverage, and regression. Bonus: Steps 10–11 sensor scan and DWR.
Scope: die-level fault detection and stack-level pattern delivery within one ATPG environment.
20